## BACKLOG
|  | Weight |  |  |  | 2 | 3 | 1
ID | Imp | Name | Notes | How to test | Estimate | Sales | Uniqueness | Cost reduction | Total value | Value percent | Cost percent | Priority | Exciter | Linear | Baseline
1 |  | As a user I want to play the songs on iPod so that I can enjoy music |  |  | 5 | 1 | 0 | 0 | 2 | 7.692% | 31.25% | 24.6154 |  |  | x
2 |  | As a user I want iPod battery to last 2 days so that I dont have to charge it that long |  |  | 1 | 1 | 0 | 0 | 2 | 7.692% | 6.25% | 123.0769 |  | x
3 |  | As a user I can navigate the iPod with a wheel so that navigation is easy |  |  | 2 | 0 | 2 | 0 | 6 | 23.08% | 12.5% | 184.6154 | x
4 |  | As a user I want iPod to jump two songs so that I can forward faster |  |  | 3 | 2 | 2 | 1 | 11 | 42.31% | 18.75% | 225.641 |  | x
5 |  | As a user I want iPod to skip songs so that I can skip something I´m not in the mood for |  |  | 5 | 0 | 1 | 2 | 5 | 19.23% | 31.25% | 61.5385 |  |  | x
[5 empty] | 16 |  |  |  | 26
Notes on importance
|  | Must be included or somebody is going to die |  |  | 500+
|  | Should be included, but we can live until next sprint |  |  | 100-499
|  | Speculative, might never be needed |  |  | 0-100
If items have same importance, they should preferably be developed in the same sprint
Note on G1: Sergey Dmitriev: By giving 2 we say that sales is more important than cost reduction, but less important than uniqueness
Note on H1: Sergey Dmitriev: I usually use numbers to state the importance of weighting criteria starting with 1 for the lowest importance and going up
Note on I1: Sergey Dmitriev: It could be that you have more weight criteria, so that you have to add som columns here
Note on F2: Sergey Dmitriev: Estimates in story points
Note on J2: Sergey Dmitriev: We calculate total value of each story by multiplying weight of each weight criteria by the relative
Note on N2: Sergey Dmitriev: Always try to deliver some of the exciters every sprint, especially on the existing products.
Note on O2: Sergey Dmitriev: Kano-weighting helps you to prioritize linear features. This is here you need this aproach the most.
Note on P2: Sergey Dmitriev: Try to do all of the baseline features. Especially on the existing products. Often no need to do the valuation on these features.
Note on H3: Sergey Dmitriev: I use numbers 0, 1 and 2 to analyse each story agains out chosen weight criteria. 0 means this story does not affect this weight criterion
Note on G4: Sergey Dmitriev: 1 means this story has slightly positive impact on this weight criterion
Note on H5: Sergey Dmitriev: 2 means this story has big impact on this weight criterion